## Project Team
ALLON FASAHA TEAM
S/N | ROLE | EXPECTED SKILLSET | NAME
1 | STAKEHOLDER | Uderstands the mission and vission of the product | LATINWO OLUGBENGA
2 | 1 PRODUCT OWNER/ PRODUCT UI/UX DESIGNER | Understand the Product development /Develop consistent User Journey/Stories/ Empathize with prospective users/ Prototyping/ SDLC Knowledge. | IBRAHIM ISMAIL
3 | ANDRIOD DEVELOPER/PROJECT LEAD | Project Management skills, Knowledge of Andrioid Engineering (Kotlin & Java), SDLC, ADLC, APIs, Database, SQLite | VICTOR LOVEDAY
4 | CONTENT CREATOR | Understand the users and have worked in similar settings (classroom). Uses and understands the UBEC Curriculum/ SDLC Knowledge. | MUKHTAR T. AMINU
5 | 2 ANIMATORS | Knowledge of Basic Adobe (Illustrator, Premier, After effects), Explandio software, Story boarding and Animation | Ibrahim Isa and Jonathan
6 | 2 VOICE OVER ARTISTS | Knowledge of Primary school content, Understand users/ have worked (Voiced) on similar Project. | RUQAYYAH TIJJANI & ZUBAIDA
7 | WEB Developer | Knowledge of HTML/CSS/PHP/MYSQL/APIs SDLC | ABUBAKAR BELLO
Stakeholders
Product
Owner
Development Team Lead
Management
Content Team Lead
Abubakar Bello
Ummi Abdulsalam
Content Creators
Content Reviewers
Static Animators
Voice over Artists
Graphics Designer
BASIRAT OYEBANKE OYEWO/ SULEIMAN ABDULLAHI
Front-End Developer (HTML/CSS)
Front-End Developer (Javascript)
Back-End Developer

## Development Plan (6 Months)
ALLON FASAHA - PRODUCT WORKPLAN (185 Days)
TASK NO | PROJECT TASK | ACTIVITY | DURATION | START DATE | END DATE | RESPONSIBILITY | STATUS
MILESTONE ONE: MODULE ONE COMPLETION
Module One (Level Two) Content
1 | Content Creation (Level Two) | Literacy Level 2 content creation |  | 2022-02-21 | 2022-03-05 | Mukthar
|  | Numeracy Level 2 content creation |  |  |  | Mukthar
|  | Content Review |  | 2022-03-07 | 2022-03-08 | Victor, Ibrahim Ismail
|  | Literacy content Adaptation |  |  |  | Product Team
|  | Numeracy content Adaptation |  |  |  | Product Team
2 | VoiceOver | Literacy Level 2 VoiceOver |  |  |  | Zubaida
|  | Numeracy Level 2 VoiceOver |  |  |  | Ruqayyah
|  | VoiceOver Reviews |  |  |  | Mukthar, Victor, Animators
3 | Animation | Literacy Content Animation |  |  |  | Jonathan
|  | Numeracy Content Animation |  |  |  | Ibrahim Isa
|  | Animated Videos Review |  |  |  | Product Team
Module One (Level Three) Content
4 | Content Creation (Level Three) | Literacy Level 3 content creation |  |  |  | Mukthar
|  | Numeracy Level 3 content creation |  |  |  | Mukthar
|  | Content Review |  |  |  | Victor, Ibrahim Ismail
|  | Literacy content Adaptation |  |  |  | Product Team
|  | Numeracy content Adaptation |  |  |  | Product Team
5 | VoiceOver | Literacy Level 2 VoiceOver |  |  |  | Zubaida
|  | Numeracy Level 2 VoiceOver |  |  |  | Ruqayyah
|  | VoiceOver Reviews |  |  |  | Mukthar, Victor, Animators
6 | Animation | Literacy Content Animation |  |  |  | Jonathan
|  | Numeracy Content Animation |  |  |  | Ibrahim Isa
|  | Animated Videos Review |  |  |  | Product Team
Platform Development
7 | Mobile App | Uploading videos onto the App |  |  |  | Victor, Abubakar Bello
|  | Review Content on the App |  |  |  | Product Team
|  | Tracing of Alphabets |  |  |  | Victor
|  | API integrations |  |  |  | Victor
|  | Playing Videos from Internal file |  |  |  | Victor
8 | Admin & Super Admin Dashboard | Dashboard UI/UX Design |  |  |  | Ibrahim
|  | Dashboard Frontend Development, API integrations and Review |  |  |  | Abu
|  | APIs Development |  |  |  | Abu
|  | Dashbaords Review |  |  |  | Victor, Abu, Ibrahim, Stakeholder
9 | Milestone Review | Final Module One Review |  |  |  | Product Team, Stakeholders
MILESTONE TWO: MODULE TWO CONTENT DEVELOPMENT & PRODUCT DEPLOYMENT
Donation Platform
10 | Requirement gathering and UI/UX Design | Requirement gathering |  |  |  | Ibrahim Ismail
|  | UI/UX Design |  |  |  | Ibrahim Ismail
|  | Design Review |  |  |  | Ibrahim Ismail, Victor, Abubakar, Stakeholder
11 | Development | Frontend Development |  |  |  | Abu
|  | Backend Development |  |  |  | Abu
|  | Platform Review |  |  |  | Abu, Victor, Ibrahim
12 | Platform Launch | Final Review |  |  |  | Ibrahim, Victor, Abu, Stakeholder
|  | Marketing and Awareness |  |  |  | Victor, Marketing Team
|  | Platform Launch |  |  |  | Victor, Marketing Team, Product Team
ALLON FASAHA DEPLOYMENT (PILOT PHASE LAUNCH)
13 | Resources | Resources listing |  |  |  | Victor, Ibrahim, Mukthar
|  | Procurement |  |  |  | Operations Dept
|  | Deployment Team Structure |  |  |  | Victor, Ibrahim, Mukthar
|  | Setup & Training |  |  |  | Victor, Mukthar
14 | Center Discovery and User Registration | Survey of Islamiyya centers, Center Selection |  |  |  | Mukthar, Ibrahim, Victor, Stakeholder, Media Team
|  | User registration |  |  |  | Mukthar, Ibrahim, Victor, Media Team
|  | Orientation |  |  |  | Mukthar, Ibrahim, Media Team
|  | Center Admin Selection and Orientation |  |  |  | Mukthar, Ibrahim, Media Team
15 | Pilot Phase Launch | Contracts/Agreements/Undertaking Signing |  |  |  | Operations Dept, HR
|  | Deployment of Resources to Centers |  |  |  | HR, Mukthar
MODULE TWO CONTENT DEVELOPMENT
17 | Content Creation | Literacy Level 1 Content Creation |  |  |  | Mukthar
|  | Numeracy Level 1 Content Creation |  |  |  | Mukthar
|  | Content Review |  |  |  | Victor, Ibrahim, Mukthar
|  | Literacy Content Adaptation |  |  |  | Product Team
|  | Numeracy Content Adaptation |  |  |  | Product Team
|  | Literacy Level 2 Content Creation |  |  |  | Mukthar
|  | Numeracy Level 2 Content Creation |  |  |  | Mukthar
|  | Content Review |  |  |  | Victor, Ibrahim, Mukthar
|  | Literacy Content Adaptation |  |  |  | Product Team
|  | Numeracy Content Adaptation |  |  |  | Product Team
|  | Literacy Level 3 Content Creation |  |  |  | Mukthar
|  | Numeracy Level 3 Content Creation |  |  |  | Mukthar
|  | Content Review |  |  |  | Victor, Ibrahim, Mukthar
|  | Literacy Content Adaptation |  |  |  | Product Team
|  | Numeracy Content Adaptation |  |  |  | Product Team
18 | VoiceOver | Literacy VoiceOver |  |  |  | Zubaida
|  | Numeracy VoiceOver |  |  |  | Ruqayyah
|  | Voiceover Review |  |  |  | Mukthar, Victor, Animators
19 | Animation | Literacy Content Animation |  |  |  | Jonathan
|  | Numeracy Content Animation |  |  |  | Ibrahim Isa
|  | Animation Review |  |  |  | Product Team
20 | Content Update | Uploading videos |  |  |  | Victor
|  | Review of Videos on Device |  |  |  | Product Team
21 | Milestone Review | Final Review for Milestone Two |  |  |  | Product Team, Stakeholders
MILESTONE THREE: MODULE THREE CONTENT DEVELOPMENT
MODULE THREE CONTENT DEVELOPMENT
17 | Content Creation | Literacy Level 1 Content Creation |  |  |  | Mukthar
|  | Numeracy Level 1 Content Creation |  |  |  | Mukthar
|  | Content Review |  |  |  | Victor, Ibrahim, Mukthar
|  | Literacy Content Adaptation |  |  |  | Product Team
|  | Numeracy Content Adaptation |  |  |  | Product Team
|  | Literacy Level 2 Content Creation |  |  |  | Mukthar
|  | Numeracy Level 2 Content Creation |  |  |  | Mukthar
|  | Content Review |  |  |  | Victor, Ibrahim, Mukthar
|  | Literacy Content Adaptation |  |  |  | Product Team
|  | Numeracy Content Adaptation |  |  |  | Product Team
|  | Literacy Level 3 Content Creation |  |  |  | Mukthar
|  | Numeracy Level 3 Content Creation |  |  |  | Mukthar
|  | Content Review |  |  |  | Victor, Ibrahim, Mukthar
|  | Literacy Content Adaptation |  |  |  | Product Team
|  | Numeracy Content Adaptation |  |  |  | Product Team
18 | VoiceOver | Literacy VoiceOver |  |  |  | Zubaida
|  | Numeracy VoiceOver |  |  |  | Ruqayyah
|  | Voiceover Review |  |  |  | Mukthar, Victor, Animators
19 | Animation | Literacy Content Animation |  |  |  | Jonathan
|  | Numeracy Content Animation |  |  |  | Ibrahim Isa
|  | Animation Review |  |  |  | Product Team
20 | Content Update | Uploading videos |  |  |  | Victor
|  | Review of Videos on Device |  |  |  | Product Team
21 | Milestone Review | Final Review for Milestone Three |  |  |  | Product Team, Stakeholders